DEVELOPMENTS IN SENIOR CYCLE RELIGIOUS EDUCATION & S.P.H.E./R.S.E.

# Commission for Evangelisation, Catechetics and Pastoral Renewal.

# Hannah Evans, Co-ordinator.

- Living Love – Senior Cycle (SPHE/RSE).

https://catholiceducation.ie/living-love-rse-resources/

4 CPD/Resource Information Sessions (one in each province)

Pilot is in currently in progress (Dec – April)

Based upon the new Senior Cycle Social, Personal and Health Education (SPHE) framework, which forms a key part of the updated Wellbeing framework, requires schools to provide a minimum of 60 hours of teaching and learning over the final two years of senior cycle education.

- Next Steps on Living Love – Senior Cycle (SPHE/RSE).

Ongoing Edits/Review and make necessary changes to resource (based on monthly feedback from educators).

April (End) - Complete Pilot.

June - Final resource to Conference and Trusts for sign-off.

July - Development of Online CPD Module & Living Love micro-site off CET website.

August – Launch of Living: Love Senior Cycle (Communication to schools) & website goes live.

September – Outreach/training with RSE teachers.

(Via Diocesan Advisors and Trusts).

Wellbeing and the Catholic School document is available to download at:

https://www.killaloediocese.ie/resources/secondary-catechetics/#collapse-29806

- Next Steps on  Senior Cycle Religious Education ‘You Matter’/‘Made for More’.

January – Consultation on Patron’s Certificate with various stakeholders.

March – Submission of Completed Made for More RE Framework and accompanying Patrons Certificate to Conference for sign-off.

April/May – Design (and Printing if needed).

June – Communication/Dissemination of Framework to Schools.

September/October – Outreach/Workshops of Made for More Framework & Patron Certificate with RE Teachers.